## Stakeholder Engagement Matrix
#VALUE!
Project Name: | Financial Q&A ChatBot
Project Manager: | Abu Bakar Siddique Al Karim
Project Phase: | Development Phase | [6 empty] | Daily | Email
Last Update Date: | 29-01-2024 | [6 empty] | Weekly | Instant Message(IM)
Stakeholder Identification |  |  |  |  | Communication Plan |  |  | Bi-weekly | Online Phone Call
Stakeholder Name | Stakeholder Role | Stakeholder Category | Level of Engangement | Influence Level | Frequency | Method of Communication | Information Type | Monthly | Online Video Call
Ms. Jashanpreet Kaur | Quality Assurance (QA) Lead | Internal | Leading | Very High | Daily | Phone Text Message | Daily status update | Bi-monthly | Phone Call
Ms. Liniya Sheen | Deployment and DevOps Engineer | Internal | Leading | Very High | Daily | Phone Text Message | Daily status update | Quarterly | Phone Text Message
Mr. Asitkumar Patel | Data Scientist | Internal | Leading | Very High | Daily | Phone Text Message | Daily status update
Mr. Neel Dharmendra Patel | UI/UX Designer | Internal | Leading | Very High | Daily | Phone Text Message | Daily status update
Mr. Usman Ahmed | Project Advisor | External | Supporting | Very High | Weekly | Email | Progress report, deliverable updates
[10 empty] | Leading | Very High
[10 empty] | Supporting | High
[10 empty] | Neutral | Medium
[10 empty] | Resistant | Low
[10 empty] | Unaware | Very Low
Internal
External
Note on C8: Project Stakeholer Role: Define the role of each stakeholder on the project (e.g. resource manager, project sponsor, technical architect, developer etc.,)
Note on D8: Stakeholder Category: Identify the category for each stakeholder: Internal Stakeholders: These are individuals/organizations that are involved in the project from within the company (e,g., project manager, sponser, project team etc.). External stakeholders: These individuals/organizations that are affected by the project’s outcome even though they are not involved in the project directly (e.g. contractors, government agencies, suppliers, sub-contractors, end users e.t.c.)
Note on E8: Level Of Engagement: Identify the level of engangement for each stakeholder: Leading: A leading stakeholder is aware of the project’s impact and is actively involved. Supporting: A supporting stakeholder is aware of the project’s impact and supports the project. Neutral: A neutral stakeholder is aware of the project’s impact but neither resists nor supports the project. Resistant: A resistant stakeholder is aware of the project’s impact but resists change. Unaware: An unaware stakeholder doesn’t know about the project or its impact.
Note on F8: Level Of Influence: Identify the level of influence for each stakeholder by selecting: Very high: A stakeholder with very high influence has a significant amount of control over key project decisions. High: A stakeholder with high influence can cause others to take action. Medium: A stakeholder with medium influence is often part of the decision-making process. Low: A stakeholder with low influence can offer opinions on decisions and express their concerns, but you may not always take their ideas into consideration. Very low: A stakeholder with very low influence can engage in the project when they desire, but they won’t have control over any decisions.
Note on G8: Frequency of communication: Identify the frequency of communication for each stakeholder (eg. Weekly, daily, as needed, monthly, bi-weekly etc.)
Note on H8: Method of Communication:. Identify the communication channel preferred by each stakeholder(eg, email, zoom, meeting ect.,)
Note on I8: Information Type: Identify the type of information that will be needed by each stakeholder (e. g. project status report, project check-ins, budget report, milestones and deliverables updates etc.,)